## Threat Matrix
Threat ID | Threat Scenario | Affected System / Asset | Threat Actor | Likelihood | Impact | Risk Level | Planned Mitigation / Control | Owner | Status
TM-01 | Unauthorized access to internal AI tools due to weak access control | All in-scope AI systems | External attackers / unauthorized internal user | Medium | High | High | Enforce RBAC, MFA, periodic access review, and admin separation | IT Security Manager | Open
TM-02 | Sensitive employee information exposed through AI prompts or outputs | Internal HR Assistant / HR Data | Internal User / careless employee | Medium | High | High | Apply data classification, output review, prompt handling guidance, and restricted access | HR Systems Manager | Open
TM-03 | Prompt injections cause the chatbot to ignore restrictions or reveal internal information | internal Knowledge chatbot / Knowledge base | Malicious User | High | High | High | Implement prompt filtering, input validation, content restrictions, and monitoring | AI Application Owner | Open
TM-04 | Customer account data is exposed through AI-assisted response drafting | Customer Support Copilot / Customer Support Data | Internal user / external attacker | Medium | High | High | Enforce human review, data protection controls, logging, and least privilege access | Support Operations Lead | Open
TM-05 | Suspicious or compromised account activity affects security AI workflows | Security Alert Triage Assistant / Security Logs | External attacker / compromised insider account | Medium | High | High | Require MFA, privileged access control, logging, and alert review for abnormal behavior | SOC Manager | Open
TM-06 | Third-party AI or API provider introduces downstream security risk | Third-Party AI / API Services | Vendor compromise / third-party failure | Medium | High | High | Perform vendor security review, contract review, and periodic reassessment | Vendor Risk Manager | Open
TM-07 | AI outputs are used without sufficient human review in a high-impact decision process | HR Assistant / Security Alert Triage Assistant / Customer Support Copilot | Internal staff overreliance | Medium | Medium | Medium | Require documented human oversight and approval for high-impact use cases | Business Process Owner | Open
TM-08 | Lack of logging and monitoring delays detection of AI misuse or data exposure | Logs / Monitoring Records / All AI systems | Internal weakness / attacker activity | Medium | High | High | Enable centralized logging, alerting, and periodic review of AI system activity | Security Operations Lead | Open

## Security Control Matrix
Control ID | Control Domain | Control Objective | Security Control | Applies To | Risk Addressed | Owner | Implementation Status | Priority | Notes
AIS-01 | Identity and Access Management | Restrict AI system access to authorized users only | Enforce role-based access control (RBAC) for all AI tools and supporting platforms | All in-scope AI systems | Unauthorized access | IT Security Manager | Planned | High | Foundational access control for the AI environment
AIS-02 | Identity and Access Management | Strengthen authentication for sensitive AI systems | Require MFA for users and administrators accessing AI systems | All in-scope AI systems | Account compromise | IT Security Manager | Planned | High | Especially important for administrative and high-impact systems
AIS-03 | Identity and Access Management | Limit privileged activity | Separate admin roles from standard user roles and review privileged access regularly | All in-scope AI systems | Excessive permissions | IT Security Manager | Planned | High | Supports accountability and reduces misuse risk
AIS-04 | Data Protection | Protect sensitive data from improper use | Classify data used in prompts, outputs, and connected knowledge sources | HR Assistant, Customer Support Copilot, Internal Knowledge Chatbot | Sensitive data leakage | Data Governance Lead | Planned | High | Helps determine handling and protection requirements
AIS-05 | Data Protection | Reduce exposure of regulated or confidential data | Prohibit entry of restricted data into unapproved public AI tools | All in-scope AI systems | Data leakage to external tools | Compliance Lead | Planned | High | Requires policy and user awareness support
AIS-06 | Data Protection | Protect stored AI-related records | Encrypt prompt logs, output logs, and connected data stores where appropriate | All in-scope AI systems | Unauthorized data access | Platform Security Lead | Planned | Medium | Especially important for logs containing sensitive records
AIS-07 | Model and Application Security | Reduce prompt-based manipulation | Implement prompt filtering, input validation, and content restriction controls | Customer Support Copilot, Internal Knowledge Chatbot | Prompt injection | AI Application Owner | Planned | High | One of the most important AI-specific controls
AIS-08 | Model and Application Security | Limit unsafe or unreliable outputs | Require output review or validation for high-impact use cases | HR Assistant, Security Alert Triage Assistant | Unsafe output / poor oversight | Business Process Owner | Planned | High | Supports human review in critical workflows
AIS-09 | Model and Application Security | Control system changes | Require change review for model settings, prompts, plugins, and connected data sources | All in-scope AI systems | Uncontrolled changes | AI Platform Owner | Planned | Medium | Helps prevent undocumented risk introduction
AIS-10 | Monitoring and Logging | Improve visibility into AI activity | Log high-risk prompts, administrative actions, policy violations, and system events | All in-scope AI systems | Weak monitoring | Security Operations Lead | Planned | High | Supports detection, investigation, and auditability
AIS-11 | Monitoring and Logging | Detect suspicious behavior early | Alert on abnormal usage patterns, excessive queries, failed access attempts, or policy bypass attempts | All in-scope AI systems | Misuse / suspicious behavior | Security Operations Lead | Planned | High | Key detective control for AI misuse
AIS-12 | Human Oversight | Ensure humans remain in control of high-impact decisions | Require documented human review before AI output is used for HR, security, or sensitive support actions | HR Assistant, Security Alert Triage Assistant, Customer Support Copilot | Overreliance on AI | Business Process Owner | Planned | High | Important for reducing decision risk
AIS-13 | Vendor Security | Reduce third-party AI risk | Perform vendor security review before approving external AI tools or integrations | Vendor-supported AI systems | Vendor compromise / weak assurance | Vendor Risk Manager | Planned | High | Applies before use and during reassessment
AIS-14 | Vendor Security | Strengthen third-party governance | Review vendor contracts for data handling, retention, access, and incident notification requirements | Vendor-supported AI systems | External data exposure | Vendor Risk Manager | Planned | Medium | Helps reduce legal and operational exposure
AIS-15 | Incident Response | Prepare for AI security events | Define AI-specific incident response steps for misuse, leakage, unsafe output, and third-party compromise | All in-scope AI systems | Delayed response | AI Security / GRC Workflow Analyst | Planned | High | Connects security incidents back to governance and remediation